Guide 2. APT Project Development

Capstone Course

1. Summary of APT Project Progress

Below, you will find different fields that must be completed with the requested information.

| APT Project Progress Summary | The TUPYMEGESTIONA project is currently in the full execution stage of its development and implementation phase under an object-oriented layered architecture. As of the cutoff date of this report, the team has achieved the following key milestones and specific objectives: - Phase 2 Completed and Approved (Milestone 1: 09/01/2026): Elicitation and specification of 26 functional requirements and 12 non-functional requirements, drafting of the SRS report (IEEE 830 standard), design of responsive navigable prototypes in Figma, and formulation of the Software Architecture Document (SAD). - Data Model and Persistence (Completed): Design of the relational multi-company, multi-branch, and multi-warehouse model, alongside the execution of DDL scripts and SQL stored procedures/routines to guarantee transactional consistency of stock. - Secondary Application - Maintainers/Backoffice (Milestone 2: 09/22/2026 - Completed): The administrative backoffice system managing companies, branches, warehouses, users, roles, and payment methods was fully built and deployed. - Primary Business Application (Milestone 3: 10/20/2026 - In Progress): The public product catalog module and sales order registration have been implemented. The team is currently advancing the warehouse inventory tracking and adjustment logic prior to the integration with Mercado Pago. |
| --- | --- |
| Objectives | The general objective and the five specific objectives defined in Phase 1 remain fully effective, focused on the development of the two interconnected applications, the integration with Mercado Pago Sandbox, PDF/Excel automated reporting, and quality assurance with a minimum test coverage of 70%. |
| Methodology | The project will be approached through a classic method, with a mix of incremental development by stages and modules. Roles remain assigned as follows: Betzabe Ruiz (Project Manager), Felipe Arcos (Systems Analyst / Frontend Developer), Sebastian Urrutia (DBA / Backend Developer), and Matías Recabarren (QA / Security Engineer). |
| Progress Evidences | - Logical Database Diagram and DDL/DML Scripts: Implemented relational model with dedicated tables for multi-company, warehouses, and orders, along with stored routines for transactional inventory control. - Code Repository (GitHub): Branch and commit history reflecting the layered architecture, showing controllers and service layers for the Secondary Application (maintainers). - Screenshots and Functional Demonstration of the Secondary Application: Operational UI views of user management with role-based access control (RBAC), warehouse parameters, and affiliated company records. - Primary Application Development Progress: Active UI views of the public catalog and sales order placement modules in local staging environments. - Quality Assurance Measures: Quality is enforced through strict separation of concerns (decoupled architectural layers), peer code reviews (pull requests), and manual constraint validation on the database schema to eliminate stock discrepancies |

2. Work Plan Monitoring

Carefully review your work plan, focusing particularly on the progress status and adjustments columns.

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or Competency Units | Activities | Resources | Activity Timeline | Person in Charge | Notes | Progress Status | Adjustments |
| - IT Project Management - Provide Solution Proposals / Communication - Architectural Modeling / Project Management - Architectural Modeling - Database Modeling / Query Programming - Build Programs and Routines - Build Programs and Routines - Build Programs and Routines - Resolve Systemic Vulnerabilities - IT Project Management - Communication / Entrepreneurial Skills | - Development of APT Project Definition and Project Charter - Requirements Matrix and SRS Report (Milestone 1) - UI Mockup Prototyping, Gantt Chart, WBS, and Use Cases - Software Architecture Document (SAD) - Database Model, Schema Tables, and Transactional Routines - Secondary App Development: Maintainers (Milestone 2) - Primary App Development: Catalog, Sales, and Stock (Milestone 3) - Mercado Pago Sandbox Integration and Reporting (Milestone 4) - Test Plan and QA Security Assurance - Change Control Matrix and Scope Verification (100% FR) - User Manuals, Final Report, and APT Defense (Milestone 5) | - Duoc UC guidelines, word processor - Excel spreadsheet, IEEE 830 standard - Figma, Excel, Use Case templates - UML modeling software, PC workstation - Relational RDBMS server, SQL console - VS Code, Web Framework, GitHub - VS Code, Backend runtime, Database - Mercado Pago REST API, PDF/Excel libraries - Unit testing suites, static code analysis tools - Traceability matrix, requirements checklist - Deployed web platform, projector, academic documentation | 18-08-2026 al 24-08-2026 25-08-2026 al 01-09-2026 01-09-2026 al 08-09-2026 08-09-2026 al 15-09-2026 15-09-2026 al 22-09-2026 15-09-2026 al 22-09-2026 23-09-2026 al 20-10-2026 21-10-2026 al 17-11-2026 18-11-2026 al 01-12-2026 25-11-2026 al 05-12-2026 01-12-2026 al 15-12-2026 | Entire team / Betzabe Ruiz Felipe Arcos / Betzabe Ruiz Felipe Arcos, Betzabe Ruiz, Matías Recabarren Todo el equipo Sebastian Urrutia Felipe Arcos, Sebastian Urrutia Felipe Arcos, Sebastian Urrutia Sebastian Urrutia, Felipe Arcos Matías Recabarren Matías Recabarren, Betzabe Ruiz Entire team | Facilitated by experience gained during previous MVP research. 26 FR and 12 NFR specified; Milestone 1 formally approved. Enabled early validation of responsive UI/UX design. Defined layered design and decoupling between both applications. Successfully resolved multi-branch and multi-warehouse relational dependencies. Milestone 2 delivered on schedule; administrative modules fully functional. Catalog and checkout modules ready; completing warehouse traceability routines. Requires sandbox credentials and webhook callback testing. Target: test coverage ≥ 70% and zero critical security vulnerabilities. Formal verification of all 26 committed functional requirements. Graduation defense before the Duoc UC academic evaluation committee. | Completed Completed Completed Completed Completed Completed In Progress Not Started Not Started Not Started Not Started | None None None None None None None None None None None |

3. Adjustments Based on Monitoring

Elaborate on your work plan observations. Analyze the planned activities and indicate which factors facilitated or hindered plan execution. Explain how you addressed or will address any obstacles, and finally state any adjustments made to the work plan based on this analysis.

### Factors Facilitating and/or Hindering Work Plan Execution - Facilitating Factors: - Adopting a decoupled two-application architecture (Primary and Secondary) enabled parallel execution on the backoffice modules without blocking frontend catalog views designed for end users. - Having prior baseline approval of all 26 functional requirements and high-fidelity Figma mockups minimized requirements ambiguity during frontend controller and layout development. - High team commitment and milestone punctuality, maintaining a Schedule Performance Index (SPI) close to 1.0. - Hindering Factors and Implemented Solutions: - Complexity in Multi-Company / Multi-Warehouse Relational Logic: Managing relationships across distinct branches and inventory bins while preserving referential integrity required extended debugging in SQL scripts. Solution: Sebastian Urrutia developed automated validation routines and database triggers to isolate stock calculations per warehouse entity. - Order Lifecycle State Management: Asynchronous order transitions between checkout, payment validation, and warehouse dispatch created duplicate status flags. Solution: The backend team standardized a finite-state machine pattern within the service layer matching the approved use-case specifications.

No activities have been removed, and no scope adjustments were necessary. All 26 functional requirements specified in the SRS report remain 100% committed. Justification: The schedule has remained predictable due to the thoroughness of Phase 1 planning (pre-validated SAD, WBS, and Gantt charts), allowing database schema creation and backoffice development to finish within their planned deadlines for Milestones 1 and 2.

### Activities Not Yet Started or Delayed - Not Started Activities (According to Schedule): - QA Test Plan, Security Hardening, and Change Control Matrix (Weeks 14 to 16): Scheduled for November 18, once all third-party integrations are active, targeting a backend test coverage of at least 70% with zero critical vulnerabilities. - User Manuals, Final Report, and Project Capstone Defense (Milestone 5 - Weeks 16 to 18): Scheduled for December 2026 to conclude the formal graduation cycle. - Strategies to Ensure On-Time Delivery: - Utilization of the schedule and cost contingency reserves established in the Project Charter. - Early unit testing executed incrementally by Matías Recabarren to avoid bottlenecks during the final QA integration window. - Weekly sprint tracking led by Betzabe Ruiz.